SHIIAN workplan 2020/21 – updated Dec 2020

| Objective | Activities | Resources | Milestones | Updates to Dec 2020 |
| --- | --- | --- | --- | --- |
| Main work projects to be delivered |  |
| Ensure smooth handover of an HiAP approach into Public Health Scotland | Meetings Training/support for relevant staff | Time - chair | Responses as appropriate Training tbc | Have met with PHS colleagues, Completed HIA of physical distancing Contributions to Social and System Recovery (SSR) work Contributions to Health and Planning WG including Place and Health themes Various other ad hoc contributions to groups |
| Lead SSR Transport group - deliver reports and briefings on links to health and recommendations to mitigate transport related health impacts of pandemic | Regular group meetings Evidence review | Time – chair, other group members, PHS staff | Reports and briefings from group | Regular meetings, main group and data & evidence subgroup Good partnership working in the group Updated impacts table with recommendations First briefing and report on links to health completed Set of interventions identified for evidence review Started HIA of road reallocation – scoping completed, working on review |
| As member of SSR E&S group, ensure recommendations address range of relevant health impacts | Regular group meetings Scoping workshops |  | Inputs to reports as appropriate | Regular group meetings Two scoping exercises held and reports published, which informed guidance |
| Scope health impacts associated with Planning scenarios | Scoping workshops Follow up evidence reviews | Time – chair and group members Support from UNCOVER at UoE Support for other evidence reviews tba | Complete scoping workshops – an LDP, a masterplan, a regional framework Follow up reviews as appropriate | Report of workshops on CEC scenarios completed UNCOVER review of housing/neighbourhood design and covid19 transmission almost completed First scoping of Adrossan North Shore development framework held, second planned Plan to do further scoping assessment of a regional planning framework |
| Health Impact Review of Working from home | Scoping workshop Evidence review Produce final report | Time – StR as lead author, chair | Completed scoping exercise Evidence reviews Complete publication | Scoping exercise held, report in publication Planning to use WHIASU HIA and produce tartanised publication |
| Build capacity for HiAP in wider PH system | Training and support for relevant staff in Boards Continue input to FPH advocacy group on HiAP Participate in and support HiAP group Scoping of capacity for HiAP | Time – chair, StR | Training/ ad hoc advice and support delivered Report on HiAP capacity | Most of this is on hold due to pandemic Ad hoc advice – various Presentations - various |
| Delivery depending on resources and opportunities |  |
| Develop short guide on HIA of ATRs and PRs (follow up to ScotPH work on Community Empowerment) | Short guide | Time - lead author, chair, ScotPHN staff | Guide completed |  |
| Complete project with SMASH to expand consideration of environmental impacts in HIA/HIIA | Revise checklist and pilot | Time – chair, SMASH/ NHSB colleagues | Report on pilot |  |
| Establish need for resource for HiAP work on economic policies | Scope potential for HIA guide on economic development | Time – needs lead author | Scoping paper completed |  |
|  | Maintenance |  |
| Highlight and support SHIIAN resources | Maintain website Email updates | Time – chair and ScotPHN team | Email updates - quarterly |  |
| Maintain network | SHIIAN meetings | Time – SG members | At least three Steering Group meetings per year |  |